## Project Planner
Block-chain Immigration Project Plan
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84
Inception | 1 | 10 | 1 | 10 | 100%
Project Outline | 6 | 5 | 6 | 5 | 100%
Project Proposal | 11 | 1 | 11 | 1 | 100%
Design - Use Case | 12 | 3 | 0 | 0 | 0%
Design - Data Flow Diagram | 15 | 3 | 0 | 0 | 0%
Design - Entity Relationship Diagram | 18 | 3 | 0 | 0 | 0%
Design - Sequence Diagrams | 21 | 3 | 0 | 0 | 0%
Design - UI Prototyping | 24 | 10 | 0 | 0 | 0%
Development - Smart Contract | 34 | 10 | 0 | 0 | 0%
Development - Desktop Application | 44 | 10 | 0 | 0 | 0%
Development - Mobile Application | 54 | 10 | 0 | 0 | 0%
Development - Testing | 44 | 20 | 0 | 0 | 0%
Project Presentation | 64 | 5 | 0 | 0 | 0%
Project Report | 69 | 10 | 0 | 0 | 0%